## Project Planner
SB |  | IT253 - Project Plan |  |  |  |  | Version 1 |  | 2019-03-20
Project Plan
ACTIVITY | SUB TASKS | SUB-SUB TASKS | PLANNED HOURS | ACTUAL START DATE | ACTUAL DURATION | ACTUAL COMPLETION DATE | SUBMISION DATE | TIME VARIANCE | PERCENT COMPLETE
Write Project Brief |  |  | 4 | 2019-03-10 | 3 | 2019-03-14 | 2019-03-15 | -1 | 90%
Project Plan |  |  | 1 | 2019-03-20 | 0.5 | 2010-03-20 | 2019-03-21 | -0.5 | 100%
Risk Analysis |  |  | 2 | 2019-03-20 | 1 | 2019-03-20 | 2019-03-21 | -1 | 100%
Flow chart/Navigation Map |  |  | 1 | 2019-03-20 | 0.5 | 2019-03-20 | 2019-03-21 | -0.5 | 100%
Storyboarding: | Main Menu |  | 2 |  |  |  |  | -2
| Page layout structure |  | 2 |  |  |  |  | -2
| Graphic Design |  | 2 |  |  |  |  | -2
| Video Design |  | 2 |  |  |  |  | -2
| Final Submision | [5 empty] | 2019-04-05
Create Elements | Main Menu | Graphic Elements | 1 |  |  |  |  | -1
|  | Page Layout | 1 |  |  |  |  | -1
|  | Page Content | 2 |  |  |  |  | -2
| Consumer Drone Page | Information Discovery | 1 |  |  |  |  | -1
|  | Graphic Elements | 1 |  |  |  |  | -1
|  | Page Development | 2 |  |  |  |  | -2
| Professional Drone Page | Information Discovery | 1 |  |  |  |  | -1
|  | Graphic Elements | 1 |  |  |  |  | -1
|  | Page Development | 2 |  |  |  |  | -2
| Other Drone Page | Information Discovery | 1 |  |  |  |  | -1
|  | Graphic Elements | 1 |  |  |  |  | -1
|  | Page Development | 2 |  |  |  |  | -2
| Regulations Page | Information Discovery | 1 |  |  |  |  | -1
|  | Graphic Elements | 1 |  |  |  |  | -1
|  | Page Development | 2 |  |  |  |  | -2
| Media Example Page | Information Discovery | 1 |  |  |  |  | -1
|  | Media Elements | 1 |  |  |  |  | -1
|  | Page Development | 2 |  |  |  |  | -2
| Create Main Page |  | 10 |  |  |  |  | -10
| Create Drone Relevant Pages |  | 5 |  |  |  |  | -5
| Create Regulations Page |  | 5 |  |  |  |  | -5
| Create Media Page |  | 3 |  |  |  |  | -3
| Create About Page |  | 1 |  |  |  |  | -1
| Animations/Transitions |  | 2 |  |  |  |  | -2
Prototype | Finalise Pages |  | 2 |  |  |  |  | -2
| Additional Elements |  | 5 |  |  |  |  | -5
| Testing |  | 5 |  |  |  |  | -5
Delivery | Deliver Product |  | 1 |  |  |  |  | -1
|  | TOTAL PLANNED HOURS | 79 | TOTAL VARIANCE |  |  |  | -74