## Risks
Risk Assessment Template
| Risk Statement |  | (Scale) | (Scale)
# | Condition | Consequence | Probability | Impact | Exposure | Mitigation | Contingency | Triggers
1 | Lack of access to software | Unable to complete tasks | 2 | 5 | 10 | Increase access time to software | Download software at home (if possible)
2 | File Corruption/Data lose | Unable to complete tasks | 1 | 1 | 1 | Utilise three points of backup to ensure data integrity | Start from beginning or closest backup
3 | Unable to use software due to inability/Lack of sufficient training | Unable to complete tasks | 1 | 8 | 8 | Will spend time learning how to use the tools | Will reduce design requirements
4 | Illness | Unable to complete tasks | 5 | 5 | 25 | Will stay healthy, eating healthy, regular breaks and exercise | Will rest and spend time off working on assignment | Licking keyboard
5 | School closure | Unable to finish | 1 | 8 | 8 | Will attempt to stay ahead of schedule to ensure delivery | Will finish at home | Poor weather, act of god, strike, etc
6 | Poor Productivity | Tasks completed to a poor standard | 4 | 8 | 32 | Will set schedules and block time to ensure minimum amount of work is completed | Reduce requirements and to reduce workload
7 | Copyright issues | Unable to utitlise desired resources | 1 | 2 | 2 | Will source media from authorised resources | Find backups for images | Using media from unauthroised sources
8 | Unrealistic expectations | Scope is to grand. Unable to complete all self-appointed tasks | 2 | 5 | 10 | Will limit me requirements to fit within my skill level | Submit what I have anyway. Ask Professor to reel me back in | Too many ideas
9 | No quality assurance | Poorly created final product | 3 | 8 | 24 | Will add quality checks throughout the process. Checking with peers to keep a high enough standard | Ensure the UI looks pretty, at the very least | No standards set up from the start. So storyboarding/design planning
10 | Technical debt | Things build up until it becomes unmanagable | 2 | 9 | 18 | Through thorough planning and tackling issues when the arise | Hid it and hope it doesn't blow up | Laziness
Note on D4: Articulate the scale being used for probability inside of the parenthesis. E.g. (1-100%) Note: 100% would mean the item is no longer a risk and has become a problem.
Note on E4: Articulate the scale being used for impact inside the parenthesis. E.g. (1-10). Note: scale must have the same range as the probability.
Note on A5: Use this column as the risk identifier which, allows each risk to be uniquely identified.
Note on B5: Use this column to capture the "likely cause" of the risk. Be detailed enough so that you can start forming mitigation plans.
Note on C5: Use this column to capture the result of the risk, should it happen. If the consequences cannot be mitigated, you will have to dealt with them in a contingency plan.
Note on D5: Use this column to estimate the probability the risk will occur. Suggest using a percentage-based scale (1-99%).
Note on E5: Use this column to estimate the amount of impact or severity of the risk.
Note on F5: This column is computed as probability x impact. Once all risks have been entered, sort by this column to identify your biggest risks.
Note on G5: Use this column to document what plans the team has to prevent the risk or to reduce the impact before occurance. This may require creating a separate, more detailed plan.
Note on H5: Use this column to identify what will need to be done if the risk becomes reality. This may require creating a separate, more detailed plan.
Note on I5: Use this column to identify what would prompt you to execute the contingency plan. A trigger is usually a date or some sort of threshold.

## Disclaimer
Ó 2002 Microsoft Corporation. All rights reserved.
The information contained in this document represents the current view of Microsoft Corporation on the issues discussed as of the date of publication. Because Microsoft must respond to changing market conditions, it should not be interpreted to be a commitment on the part of Microsoft, and Microsoft cannot guarantee the accuracy of any information presented after the date of publication.
This document is for informational purposes only. MICROSOFT MAKES NO WARRANTIES, EXPRESS OR IMPLIED, IN THIS DOCUMENT.